## event planning checklist
Stay Perfectly Connected at Your Event with Rent2way
Event Planning Checklist
Initial Planning Phase
Task | Done? | Assignee | Due Date | Notes
8-12 Weeks Before
Define event goals, target audience, and key performance indicators
Establish total budget with contingency funds
Research and book venue with capacity for expected attendance
Build a detailed schedule with important deadlines for each task.
Plan out the event’s content and activities.
Identify and contact potential speakers/presenters.
Research and select event management software/tools
Draft sponsorship options and begin reaching out to potential sponsors.
Secure event insurance coverage
Assemble core planning team and assign responsibilities
Create a strategy for promoting the event, including timelines for social media and other channels.
Develop branded event materials (logo, theme, color scheme)
Book accommodations block for out-of-town attendees/speakers
6-8 Weeks Before
Finalize event agenda, schedule, and session formats
Confirm speakers/presenters and collect their materials/requirements
Contract essential vendors (catering, AV, security, cleaning)
Launch registration system and early-bird ticket sales
Begin promotional campaign across all channels
Create event website or dedicated landing page
Develop floor plan and space allocation
Order signage, badges, and printed materials
Arrange transportation logistics (shuttles, parking)
Begin weekly planning team meetings
Initiate permit applications if required
Create attendee communication plan and templates
Develop content for event app or digital guide
Confirm sponsorship commitments and deliverables
4-6 Weeks Before
Review registration numbers and adjust marketing if needed
Share event details, expectations, and logistics with confirmed speakers and presenters.
Finalize menu selections with caterer
Develop a precise schedule with timing for each part of the event
Set up social media event pages and hashtag strategy
Schedule pre-event promotional content
Organize staff/volunteer training sessions
Create emergency response plan and communication protocols
Begin technical production planning (staging, lighting, sound)
Finalize room blocks and accommodation arrangements
Confirm your order for branded items, attendee giveaways, and event swag.
Create VIP/sponsor experience elements
Arrange photography and videography coverage
Review accessibility accommodations and requirements
Review and finalize any signage, banners, and branding that will be placed
Arrange transportation for high-priority attendees
2-3 Weeks Before
Send event reminders with final agenda to registered attendees
Schedule a walkthrough of the venue with your core planning team
Create load-in/load-out schedule with all vendors
Finalize audiovisual requirements and presentations format
Prepare speaker/VIP welcome packages
Test the registration systems, event apps, and live streaming platforms
Finalize and print name badges and print the final attendee lists
Confirm staffing assignments and create shift schedules
Confirm transportation options and routes for attendees, speakers, and VIPs.
Review and confirm signage placement around the venue
Update website with final event information
Arrange post-event evaluation system
Confirm media attendance and prepare press materials
Review security arrangements and access control protocols
1 Week Before
Send final confirmation emails with essential event details to attendees
Hold comprehensive team briefing for all staff and volunteers
Confirm final headcounts with venue and caterer
Collect and organize all presentation files in backup formats
Prepare all the registration materials and attendee packets
Prepare vendor payment envelopes and tip amounts
Create contact sheet with all key personnel and emergency numbers
Check weather forecast and adjust outdoor plans if necessary
Conduct technical rehearsals for key presentations/performances
Finalize seating/table arrangements
Prepare branded social media templates for live event coverage
Assemble emergency supply kit (first aid, tools, tech backups)
Review special accommodations requests and requirements
Schedule post-event debrief meeting with key stakeholders
Day Before
Conduct final venue walkthrough with venue manager
Confirm all deliveries and vendor arrival times for event day
Set up registration area and information stations
Test all technical equipment and backup systems
Place directional signage and branded materials
Organize VIP/speaker green room with necessary amenities
Prepare and distribute final briefing notes to staff/volunteers
Charge all communication devices and backup batteries
Review transportation schedule and confirm drivers
Prepare cash box and change if handling onsite payments
Check in with speakers/presenters and address any last-minute needs
Print final copies of run sheets, attendee lists, and seating charts
Set up early decorations and displays as permitted
Conduct security briefing and verify access control systems
Event Day
Pre-Opening (Early Morning Setup)
Arrive at venue 2-3 hours before doors open
Conduct venue safety walkthrough
Set up and test registration systems/technology
Brief all staff and volunteers on the day's schedule and responsibilities
Set up greeters at entrances to direct attendees and provide information
Test all audiovisual equipment and presentations
Check Wi-Fi and technical connectivity
Verify catering setup and food delivery
Place final signage and directional indicators
Prepare VIP/speaker holding areas
Stock information desks with materials and resources
Set up photography/videography equipment
Test emergency communication systems
Conduct final sound checks and lighting tests
Opening Hours/Registration Period
Open registration/check-in desks with full staffing
Monitor entrance flow and adjust staffing as needed
Manage early arrivals and special access requests
Brief security on VIP arrivals and protocols
Start social media coverage and announcements
Distribute welcome packages and badges
Guide exhibitors/sponsors to their locations
Appoint a team on standby to fix any registration or technical issues
Start serving early refreshments for attendees
Confirm all speakers/presenters have arrived
Activate event app push notifications
Conduct final microphone checks for opening sessions
Update digital signage with any schedule changes
Main Event Hours
Manage room transitions and timing between sessions
Coordinate speaker transitions and technical needs
Monitor attendance at various sessions/areas
Oversee meal service and refreshment breaks
Address attendee questions and special requests
Facilitate networking activities and special events
Maintain contact with venue staff for immediate needs
Collect attendee feedback throughout the event via surveys, app responses, or in-person interactions
Track social media platforms for mentions of the event
Ensure photographers and videographers are documenting key moments
Manage any medical or emergencies promptly
Update team via established communication channels
Implement contingency plans as needed
Closing/Wrap-Up
Manage closing session or keynote
Begin breakdown of non-essential areas
Distribute post-event surveys
Collect leftover materials and supplies
Secure valuable equipment and items
Thank speakers, sponsors, and key participants
Oversee vendor departure and initial load-out
Conduct lost and found collection
Hold brief end-of-day team meeting
Document any venue damages or issues
Begin social media wrap-up messaging
Secure final payments or signatures required
Thank venue staff and confirm post-event responsibilities
Organize a team celebration or acknowledgment
Post-Event (1-2 Weeks After)
Send thank-you emails to attendees, speakers, sponsors, and vendors
Collect and compile event photos and videos
Review survey results and attendee feedback
Hold a comprehensive team debrief meeting
Prepare event performance report with KPI measurements
Finalize and pay all outstanding vendor invoices
Update attendee database with new connections
Create and distribute a highlight reel or an event recap
Return any rented or borrowed equipment
Send promised materials or information to attendees
Archive event documentation and planning materials
Conduct ROI analysis for sponsors and stakeholders
Begin preliminary planning for next event, if applicable
Identify improvement opportunities from lessons learned
Recognize and reward outstanding team contributions